## Sheet1
University of Glasgow - 2022
Job no. | GLU001:28535 |  |  | Piriority for maintenance | ADNO Comments
Quote no. | Order no. | Bldg ref | Site |  |  | Site address | PM £ | Campus | Equipment |  | visits per year | Days per visit | Last visit | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01
*5804 | AMK245141 | 708 | Welpers Equine Centre | 12 | Units beond repair, not seen since survey. | 462 Bearsden Road, Glasgow, G61 1QH | 808 | Garscube | ElectroVap humidifier -Quoted to replace | 80162 | 2 | 0.5 | bar: 2022-02-01; 2022-08-01
[9 empty] | ElectroVap humidifier -Quoted to replace | 80163 | bar: 2022-02-01; 2022-08-01
*4312 | AMK245118 | 706 | Vet Research Facility | 6 | Ongoing issues with units. | Switchback Road, Bearsden, Glasgow, G61 1BD | 1896 | Garscube | RS120 | 1200629 | 2 | 1.5 | 2021-12-22 | 2022-02-01: 3days; 2022-08-01: 3days
[9 empty] | RS30 | 1217384 | bar: 2022-02-01; 2022-08-01
[9 empty] | RS30 | 1217383 | bar: 2022-02-01; 2022-08-01
*5767 | AMK245097 | 636 | Small Animal Hospital | 1 | Wetting out issues | 464 Bearsden Road, Glasgow, G61 1BD | 1088 | Garscube | RS80 | 1218491 | 2 | 1 | bar: 2022-02-01; 2022-08-01
[9 empty] | RS120 | 1218492 | bar: 2022-02-01; 2022-08-01
*5802 | AMK245090 | 323 | Saughfield Data Centre | 9 | Newer units | ?? | 808 | ? | Condair EL5 | 1213406 | 2 | 0.5 | bar: 2022-03-01; 2022-09-01
[9 empty] | Condair EL5 | 1218756 | bar: 2022-03-01; 2022-09-01
*5768 | AMK245102 | 505 | Thurso Street (Unite) | 8 | Don't think I have seen site since survey | 1-3 Thurso St, Glasgow, G11 6PE | 808 | ? | Vapac LE18PD 400v | V35377 | 2 | 0.5 | bar: 2022-03-01; 2022-09-01
[9 empty] | Vapac LE18PD 400v | V39806 | bar: 2022-03-01; 2022-09-01
*5803 | AMK245136 | 324 | Hunterian Art Gallery | 2 | Not seen since survey | 82 Hillhead St, Glasgow, G12 8QQ | 1896 | Gilmorehill | Dristeem HT 12 | N498-02-01 | 2 | 1.5 | bar: 2022-03-01; 2022-09-01
[9 empty] | HygroMatik HY1 0.5-L | 0402078 |  |  |  | 2022-03-01: 2.5 days; 2022-09-01: 2.5 days
[9 empty] | HygroMatik HY1 0.5-L | 0402077 | bar: 2022-03-01; 2022-09-01
[9 empty] | HygroMatik HY1 0.5-L | 0402079 | bar: 2022-03-01; 2022-09-01
[9 empty] | HygroMatik HY1 0.5-L | 0402080 | bar: 2022-03-01; 2022-09-01
[9 empty] | HygroMatik HY2 17EMP | 0402081 | bar: 2022-03-01; 2022-09-01
[9 empty] | HygroMatik HY2 17EMP | 0402083 | bar: 2022-03-01; 2022-09-01
[9 empty] | HygroMatikHY 17-C | 1203121 | bar: 2022-03-01; 2022-09-01
[9 empty] | HygroMatikHY1 0.8L | 03A5699 | bar: 2022-03-01; 2022-09-01
[9 empty] | HygroMatikHY1 0.8L | 03A4701 | bar: 2022-03-01; 2022-09-01
*5805 | AMK245124 | 170 | Wolfson Medical School Building | 11 | Units may be beond repair, not seen since survey. | University Ave, Glasgow, G12 8QQ | 924 | Gilmorehill | ELMC90 - Quoted to replace | 90038 | 2 | 1day | bar: 2022-04-01; 2022-10-01
[9 empty] | ELMC90 - Quoted to replace | 90030 | bar: 2022-04-01; 2022-10-01
[9 empty] | ELMC90 - Quoted to replace | 90069 | bar: 2022-04-01; 2022-10-01
*5798 | AMK245084 | 100 | JWNF - Nano Tech, James Watt Bldg | 10 | Recently visited | Engineering Way, Glasgow, G12 8QQ | 3264 | Gilmorehill | RHT - Electrovap Humidifier 8kg | 11662 | 3 | 2 | 2021-04-19 | bar: 2022-04-01; 2022-10-01
[9 empty] | RHT - Electrovap Humidifier 17kg | 11663 |  |  |  | 2022-04-01: 5days; 2022-10-01: 5days
[9 empty] | ElectroVap humidifier | 94921 | bar: 2022-04-01; 2022-10-01
[9 empty] | ElectroVap humidifier | 94922 | bar: 2022-04-01; 2022-10-01
[9 empty] | ElectroVap humidifier | 94956 | bar: 2022-04-01; 2022-10-01
[9 empty] | ElectroVap humidifier | 94958 | bar: 2022-04-01; 2022-10-01
[9 empty] | ElectroVap humidifier | 95195 | bar: 2022-04-01; 2022-10-01
[9 empty] | ElectroVap humidifier | 95127 | bar: 2022-04-01; 2022-10-01
*5799 | AMK244991 | 124 | Joseph Black | 7 | 1 visit since survey | University Ave, Glasgow, G12 8QQ | 1088 | Gilmorehill | Carel Humisteam 10 | 19216 | 2 | 1 | bar: 2022-04-01; 2022-10-01
[9 empty] | HygroMatik HL90-C | 1600834 | bar: 2022-04-01; 2022-10-01
[9 empty] | HygroMatik HL90-C | 1600836 | bar: 2022-04-01; 2022-10-01
[9 empty] | HygroMatik HL90-C | 1600831 | bar: 2022-04-01; 2022-10-01
[9 empty] | HygroMatik HL90-C | 1600833 | bar: 2022-04-01; 2022-10-01
*5801 | AMK244978 | 134 | Central Research Facility | 5 | Not seen since survey | Glasgow, G12 8QQ | 1088 | Gilmorehill | HygroMatik HY 116-C | 1700025 | 2 | 1 | bar: 2022-04-01; 2022-10-01
[9 empty] | HygroMatik HY 116-C | 1700021 | bar: 2022-04-01; 2022-10-01
[9 empty] | HygroMatik HY 116-C | 1700022 | bar: 2022-04-01; 2022-10-01
*5769 | AMK245131 | 327 | CCNI - Centre for Cognitive Neroimaging | 3 | Not seen since survey | Hillhead St, Glasgow, G12 8QE | 808 |  | EL Basic 5kg/hr 230v | 1221781 | 2 | 0.5 | bar: 2022-05-01; 2022-11-01
*4675R1 | AMK244997 | 326 | Library | 4 | Not seen since survey | Hillhead St, Glasgow, G12 8QE | 5160 | Gilmorehill | RS-OC 20 400v3 M THV UK | 1218971 | 2 | 4.5 | 2020-10-16 | bar: 2022-05-01; 2022-11-01
[9 empty] | RS-OC 20 400v3 M THV UK | 1218970 | bar: 2022-05-01; 2022-11-01
[9 empty] | RS 30kg/hr | 1218972 | bar: 2022-05-01; 2022-11-01
[9 empty] | RS10kg/hr 400v | 1218973 | bar: 2022-05-01; 2022-11-01
[9 empty] | RS10kg/hr 400v | 1218974 | bar: 2022-05-01; 2022-11-01
[9 empty] | RS8ikg/hr 400v | 1218975 | bar: 2022-05-01; 2022-11-01
[9 empty] | Carel Heatersteam (TBC) | A00026806 | bar: 2022-05-01; 2022-11-01
[9 empty] | Carel Heatersteam (TBC) | A00026745 | bar: 2022-05-01; 2022-11-01
[9 empty] | Vapac LE60 | V22601 | bar: 2022-05-01; 2022-11-01
[9 empty] | Vapac LE30 | V22602 |  |  |  | 2022-05-01: 5days; 2022-11-01: 5days
[9 empty] | Vapac LE60 | V25958 | bar: 2022-05-01; 2022-11-01
[9 empty] | Vapac LE30 | V25943 | bar: 2022-05-01; 2022-11-01
[9 empty] | Vapac LE60 | V29375 | bar: 2022-05-01; 2022-11-01
[9 empty] | Vapac LE30 | V29374 | bar: 2022-05-01; 2022-11-01
[9 empty] | Vapac WL30 - quoted to replace | V04482 | bar: 2022-05-01; 2022-11-01
[9 empty] | Vapac LRPD60 - quoted to replace | V51890 | bar: 2022-05-01; 2022-11-01
[9 empty] | Vapac WL60 - quoted to replace | V09572 | bar: 2022-05-01; 2022-11-01
[9 empty] | Vapac WL30 - quoted to replace | V10061 | bar: 2022-05-01; 2022-11-01